SOFTWARE ENGINEERING AND PROJECT MANAGEMENT

6. IT Project Management and Project Scheduling

6.1 Introduction, 4 P‘s, W5HH Principle, Need for Project Management, Project Life cycle and ITPM, Project Feasibility, RFP, PMBOK Knowledge areas, Business Case, Project Planning, Project Charter and Project Scope.

6.2 Project Scheduling: Defining a Task Set for the Software Project, Timeline charts WBS, Developing the Project Schedule, Network Diagrams (AON, AOA), CPM and PERT, Gantt Chart, Tracking the Schedule, Earned Value Analysis

PAST QUESTIONS:

- What are the different phases in project life cycle with suitable example. (M23, D23)

- Explain project scheduling and describe CPM and PERT. (M23, D23, D24)

- Explain the 4’PS of project Management. (D23)

- Define following terms: i. Project ii. Critical path iii. Earned value iv. Process v. Scope. (M24)

- Explain W5HH Principle. (M24)

- Draw AON diagram and find the critical path. Find the total float time for each path and list down the critical and non-critical activities. Find the total duration of the project? (M24)

- Short note on PMBOK Knowledge Areas. (M24)

- Discuss project management techniques. (D24)

NOTES:

*4 P’s :-

The 4 Ps of project management refer to the four key elements that project manager needs to consider and balance when managing a project. These four Ps are:

- People – The most important contribution in software project is not made by system or tools, it is done by people i.e. Humans.

The success of the project depends on selecting right kind of people with right talent.

- Product – The product is the ultimate goal of the project. This is any type of software product that has to be developed and delivered.

- Process – The team members should have a methodology and plan that complete project as per customer requirements. Without a clearly defined process, team members will not know what to do.

Using the right process will increase the project success.

- Project – The project is the complete software. The project manager plays a critical role. They are responsible to guide the team members to achieve the project’s target and objectives, helping & assisting them with issues, checking on cost and budget, and making sure that the project stays on track with the given deadlines.

*W5HH Principle :-

The W5HH principle, proposed by Barry Boehm, is a framework of questions to address key aspects of a software project plan:

- Why is the system being developed? (Justification, business case)

- What will be done? (Tasks, deliverables, scope)

- When will it be done? (Schedule, milestones)

- Who is responsible for a function? (Roles, assignments)

- Where are they organizationally located? (Team structure, stakeholders)

- How will the job be done technically and managerially? (Approach, methods)

- How much of each resource is needed? (Effort, cost)

Addressing these questions helps define the project's objectives, scope, responsibilities, schedule, approach, and resource requirements, forming a comprehensive initial plan.

*Project life cycle :-

The project life cycle is a step-by-step process that guides a project from start to finish. It includes phases like initiation, planning, execution, monitoring and closure. This process helps organize and manage project tasks, ensuring everything stays on track to meet the project's goals efficiently. By following these steps, projects are more likely to be successful and meet their objectives.

Project life cycles typically consist of five major phases:

- Initiation: This is the first phase where the project's idea is created, and its feasibility is assessed. Initial project goals, objectives, and key stakeholders are identified. This phase sets the foundation for the project, ensuring that it is viable and aligned with overall objectives before moving forward. Proper planning in this phase helps to guide the project's direction and success.

- Planning: In this phase, a detailed project plan is developed. It includes a list of tasks, a timeline for each task, how resources will be allocated, and strategies for managing risks. This plan helps keep the project organized and on track, ensuring that everyone understands their roles and responsibilities and how to handle any potential issues that might arise.

- Execution: In this phase, the project plan is put into action. The team works together to complete the tasks and produce the project's results. It’s where the real work happens, with everyone collaborating to achieve the goals and ensure the project stays on track. Regular updates and adjustments are made as needed.

- Monitoring and Controlling: In this phase, project progress is carefully monitored to ensure it follows the plan. Any deviations or issues are identified, and corrective actions are taken to address them. This helps keep the project on track and ensures that it continues to meet its goals and deadlines.

- Closure: Once the project’s deliverables are completed and approved, the project officially comes to an end. Lessons learned throughout the project are documented to help with future projects. The team and resources are then released or reassigned, and any final paperwork or administrative tasks are completed. This phase ensures everything is finalized and reviewed for future improvements.

*Project Scheduling :-

Project scheduling defines the timeline for project activities, ensuring timely completion and resource management. It involves task identification, duration estimation, sequencing, and resource allocation.

Project scheduling is the process of planning and organizing the tasks, activities, and milestones of a project along a timeline.

The purpose of project scheduling is to ensure timely completion of the project by effectively managing time, resources, and dependencies between tasks.

CPM - CPM stands for Critical Path Method. CPM is a technique that is used for projects where the time needed for completion is already known.

CPM is a technique of project management which is used to manage only certain (i.e., time is known) activities of any project. It is a deterministic model.

It is suitable for construction projects.

PERT - PERT stands for Project Evaluation and Review Technique. PERT is a technique that is used for projects where the time needed for completion is not known.

PERT is a technique of project management which is used to manage uncertain (i.e., time is not known) activities of any project. It is a probability model.

It is suitable for projects which required research and development.